## Sheet1
ID | Work Item Type | Title 1 | Title 2 | Original Estimate | Completed Work | Remaining Work | State
| User Story | [5 empty] | New
| Task | Implement the data-handling algorithms. |  |  |  |  | Done
| Task |  | Implement the Quicksort Algorithm, for sorting the vectors that house the programme's data. | 1 | 1 | 0 | Done
| Task |  | Implement the searching algorithm, for searching the sorted vectors of data. | 2 | 1 | 0 | Done
| Task | Implement the classes. |  |  |  |  | Done
| Task |  | Make the appointment class, for handling appointment-related data. | 1 | 1 | 0 | Done
| Task |  | Make the people super-class, for handling the properties of individuals and allowing the subclasses to inherit from the superclass. | 2 | 1 | 0 | Done
| Task |  | Make the Dentist sub-class. | 2 | 1 | 0 | Done
| Task |  | Make the Patient sub-class. | 2 | 1 | 0 | Done
| Task |  | Make the Room class. | 1 | 1 | 0 | Done
| Task | Create the interface. |  |  |  |  | Done
| Task |  | Make functions for interface navigation. | 4 | 1 | 0 | Done
| Task |  | Make functions for input validation. | 2 | 1 | 0 | Done
| Task |  | Make the interface class. | 4 | 1 | 0 | Done
| Task | Handle the data. |  |  |  |  | New
| Task |  | Make the .csv files. | 1 | 1 | 0 | Done
| Task |  | Make the CSV_Reader class. | 2 | 1 | 0 | Done
| Task |  | Make the Data class, for storing vectors that contain pointers to instances of the other classes. | 3 | 1 | 0 | Done
| Task |  | Add the ability to write to the .csv files. | 2 | 0 | 1 | New
| Task | Address the use cases. |  |  |  |  | New
| Task |  | Add the ability to view the data. | 2 | 1 | 0 | Done
| Task |  | Add the ability to view the time and date. | 1 | 1 | 0 | Done
| Task |  | Add the ability to book appointments. | 5 | 0.8 | 0.2 | New
| Task |  | Add the ability to book follow-up appointments. | 2 | 0 | 1 | New
| Task | Test the programme. |  |  |  |  | New
| Task |  | Create test cases for the classes. | 1 | 0 | 1 | New
| Task |  | Create test cases for the non-class-based functions. | 1 | 0 | 1 | New
| Task | Create the Makefile. |  |  |  |  | New
| Task |  | Configure the Makefile to compile the Dentist Programme. | 1 | 1 | 0 | Done
| Task |  | Configure the Makefile to compile the quicksort testing programme. | 1 | 1 | 0 | Done
| Task |  | Configure the Makefile to compile the Catch2 testing programme. | 1 | 0 | 1 | New
| Task |  | Include the class files (as .o files) in the Makefile. | 1 | 1 | 0 | Done